## STATEMENT OF WORK METHOD

### NATURE OF WORKS:

## “River bank protection work of Tetulia river (Right Bank) from Km 3.000 to Km 3.300 total 0.300 Km at Mehendigonj upazila of
Barishal district in c/w "River bank protection work at different location of Mehendigonj upazilla from erosion of Tetulia river in
Barishal district" under Barishal WD Division, BWDB, Barishal.” (e-Tender ID: 1264860, Package No: BSL/MHDJ/WD-11)

## INTRODUCTION

This work method statement outlines the proposed approach for the successful execution of the river bank protection works along the Padma River. The methodology is indicative and subject to adjustment based on practical site conditions and as approved by the Engineer-in-Charge. It is prepared based on the information provided in the Tender Documents and reflects our understanding of the project requirements. Our planning will utilize the Critical Path Method (CPM) to ensure efficient scheduling, monitoring, and control of all project activities. We have extensive experience in executing similar large-scale river bank protection works under the Bangladesh Water Development Board (BWDB) and are confident in our ability to deliver this project to the highest standards of quality and timeliness.

## PREPARATION OF MOBILIZATION

Upon signing the Contract Agreement, we will immediately commence mobilization of all necessary personnel, equipment, and materials to the site. A site office will be established to accommodate the Project Manager, engineers, surveyors, and support staff. This will be supplemented by a labor shed, material storage yard, and necessary utilities including a tube-well for fresh water and sanitary facilities. The site office will be equipped with a field laboratory for conducting random tests on construction materials to ensure quality compliance.

## MAJOR COMPONENTS OF WORK

Mobilization of manpower, equipment, and materials.

Site Preparation, including clearing and pre-work surveys.

Earthwork in cutting & filling to design slope.

Geo-Textile Filter and Sand Filter laying.

C.C. Block Manufacturing and Curing.

C.C. Block Dumping & Placing on the prepared slope.

De-mobilization & Site Handover to the Procuring Entity.

SITE FACILITIES:

Generally, for construction of site office we have leased some suitable place:

1. Site Office: The site office will cover an area of 150 Sqm. constructed by Tin shed for use of the owner and our high official with full facilities of office works. All furniture utilities and first aid’ box will be arranged during the whole construction period.

2. Staff and Labour shed of an area about 100 Sqm: It will be constructed by tin shed for use of all staff and low-level officer of the Firm. We the contractor shall provide and maintain necessary living accommodation and ancillary facilities for labour at our own expenses to standards and scales approved by the engineer.

3. Store of an area about 100 sqm has been constructed by tin shed for storage of cement and other construction equipment. It will be always kept in dry condition

4. Proper sanitation and water supply system have been provided at site. 2 Nos Sanitary Latrine are provided & Tube well is provided for sweet water.

## EQUIPMENT MOBILIZATION

The following major construction equipment, as specified in the Tender Data Sheet, will be mobilized to the site. All equipment will be in full working order.

| No | Equipment Type and Characteristics | Minimum Number Required |
| --- | --- | --- |
| 1 | Concrete Mixture Machine (Full Cement Bag Capacity) | 4 Nos |
| 2 | Vibrator Machine | 4 nos |
| 3 | Form Work for CC Block | 3000 nos |
| 4 | Weight Machine | 2 nos |
| 5 | Sewing Machine | 4 nos |
| 6 | Excavator | 2 nos |
| 7 | Generator | 2 Nos |
| 8 | Pump Machine | 2 Nos |
| 9 | Survey Instrument | 1 Set |
| 10 | Engine Boat | 4 Nos |
| 11 | Dumping Berge | 2 Nos |

## METHODOLOGY OF WORKS

### A. Monitoring and Quality Control

Continuous monitoring will be essential. Weekly and monthly progress reports will be prepared to assess project status. A robust quality control system will be implemented, with trained technical personnel overseeing all stages. All materials (cement, aggregates, sand, geo-textile) will be inspected and tested to ensure they comply with specified requirements before use.

B. Quality Control

Quality control is most essential for ensuring safety of the structure. For making quality control, trained technical personnel will be engaged during execution of work. All the materials to be used in construction will be inspected and examined to ensure that they comply with their specified requirement.

The Engineer in charge make any test of sand, stone chips, cement, and if the considers necessary to re ascertain the quality of requisite materials Any material which, in the opinion of the Engineer, is of doubtful quality shall not be used in the Works until it has been re-tested and test result sheets, showing that in complies in all respects with the relevant standard have been delivered to and accepted by the Engineer.

### C. Earthwork in Cutting & Filling

Earthworks will involve constructing the design slope as per the drawings. The material used for fill will be suitable earth, free from organic matter, and approved by the Engineer. Compaction will be done in layers to achieve the required density. After slope preparation, geo-textile and sand filter layers will be placed as per specifications to ensure proper drainage and stability.

### C. Concrete Production (C.C. Block)

C.C. blocks will be manufactured at a dedicated casting yard on-site.

Materials:  Cement will be Portland cement (ASTM C 150 Type 1 or equivalent). Aggregates will be hard, durable, and clean. Fine aggregates (sand) will have a fineness modulus as specified. Water will be clean and free from impurities.

Mixing:  Concrete will be mixed using mechanical mixers to the approved design mix ratio to achieve the required compressive strength.

Casting:  Steel formwork will be used to ensure uniform shape and size. Concrete will be poured and compacted using vibrators.

Curing:  Blocks will be cured for a minimum of 21 days by keeping them continuously wet. Each block will be marked with the date of casting for quality tracking.

Steel Form work will be manufactured to ensure designed shapes and size of block.

Concreting will be done properly & compacted by needle vibrators. Coarse Aggregate will be washed before pouring into the Mixture Machine. Cement will be mixed on full load. Sufficient water will be mixed to maintain 50mm to 60mm Slump. Concrete will be poured into shutter from a high less than 1 meter. The casting yard where shutters to be set will be compacted, leveled to prohibit leakage of cement paste & sufficient drainage systems will be established to avoid water logging. Gaps between shutters will be remedied using putty or polythene. Produced CC Block shall be protected from the effects of sunshine, dry wind, rain, running water or mechanical damages for a continuous period

Curing of CC blocks will be will be done for a continuous period of twenty-one days. Blocks will be kept continuously wet; Blocks will not be stockpiled until they have been cured for at least 7 days. Each block will be marked with a consecutive number and date of casting. Then will be stockpiled with consecutive numbers and in measurable stack.

The curing of concrete which has achieved it final set shall be by one more of the following methods:

By water spray in continuous operation or a layer water,

By covering with Hessian or similar absorbent materials, or sand, kept constantly wet;

After trough wetting, by covering with a layer of waterproof fabric kept in contact with the concrete surface.

Saline water will not use for curing purpose.

During testing of CC block field test of cement concrete

The sampling of concrete will be made to ascertain the quality of CC block. Concrete cylinders will be undertaken at the place of depositions of the concrete. Each sampling will provide sufficient concrete to make six cylinders and allow a slump test; Samples will be taken for each 20 cum of concrete bathed cylinders will be tested if desired by the employer.

### D. Geo-Textile Sheet Storage and Handling

Geo-textile rolls will be stored under cover, protected from direct sunlight and physical damage. They will be handled carefully to prevent tears. Lapping and anchoring will be done as per the Engineer's instructions during placement on the prepared bank slope.

### E. Dumping & Laying of C.C. Blocks

After proper curing and approval, C.C. blocks will be transported from the stack yard to the placement site using barges and other suitable means. Blocks will be carefully placed on the filter layers, starting from the toe and working up the slope, to form an interlocked, stable revetment. Placement will be guided by survey controls to ensure adherence to the design lines and levels.

F. GEO-TEXTILE BAGS FILLING:

(i)	Detailed description of how the bags will be filled including the type and numbers of technical/mechanical filling devices if any.

(ii)	Bags will be dumped only when Dumping Locations/positions will be fixed by Total station.

(iii) 	Type, source and quantity of sewing machines, and power sources and sewing capacity.

(iv) 	Type, source and quality certificates of thread including supplier’s name.

(v) 	Anticipated daily production rate.

G. TRANSPORT OF GEO-TEXTILE BAGS:

Description of the number of power driven flat top boat to be used, including their dimensions and capacities. [It is important that height of boat and its draft is matched for easy loading and unloading sandbags]

(i) Description of propulsion devices for boat, (if not self-propelled) their capacity (horsepower).

(ii) Description of loading cycle including capacity of manpower time etc.

H. METHOD OF EXCAVATION:

(i) The method of excavation of river bank slope above and below low water level.

(ii) Use of equipment for the purpose of excavation.

(i) Details of positioning system and data storage, including type of equipment

(for example, total station) and expected survey tolerances.

I. DUMPING OF GEO-TEXTILE BAGS:

(i) Description of dumping mechanism and equipment to dump the geo-bags at the slope and berm of the river slope toe including positioning by Total Station and dumping aid (e.g. floating).

(ii) Details of positioning system and data storage, including type of equipment (for example total station) and expected survey tolerances.

(iii) Dumping methodology including the average daily capacity for the relevant placement methods described in Section 1.5. This should include the proposed number of labor, the time to dump the required number of bags, the time to move empty boat back for loading, loading time, and time for movement to dumping pontoon for next cycle.

(iv) Method of ensuring that bags are dumped in the required number in the specified locations (as per this sub-clause reference 1.10 and sub-clause 1.5 of Technical Specifications).

(iv)	Details of records of positioning dumping equipment and number of dumped bags.

## DEMOBILIZATION

On completion of the works: we the contractor at our own expenses shall remove all temporary structure likely site office, stores, site laboratory etc, and remove all debris, false works, equipments machineries and other materials like surplus sand, surplus geo-textile & surplus stone and other rubbish etc. From the right of way and from any property defaced or occupied by us in connection with the contract works and shall leave site in neat and tidily condition to the satisfaction of the Engineer in-charge.

The Construction Agency will be bound to follow the construction rule during execution period. The Construction Project Manager/Engineer-in-charge should be most efficient & hard-working person who will maintain liaison with the Owner & Consultant always.

To ascertain our ability to complete the New Bank Protective work necessary papers regarding solvency concern, construction equipment, efficient man power/ engineers as well as time schedule furnished herewith the tender as wanted.

The successful completion of the project completely lies on a good Manager/ Engineer-in- charge & Teamwork.

(Mahmudul Hassan)

Proprietor